## Slide 1
INNER-CITY MUSLIM ACTION NETWORK
IMAN Knowledge Map
Five Milestones Complete:
The Research-to-Action Infrastructure Is Built
Chicago, IL · April 2026
LOGO /
SCREENSHOT

## Slide 2
Three Questions This Deck Answers
2 / 11
01
What problem are we solving?
A 30-year life expectancy gap and the bottleneck between evidence and action
02
What has been built so far?
5 milestones: structured research library, cloud access, team environment, IMAN data integration, and expert outreach
03
What comes next?
4 capabilities in development to fully operationalize the system
SCREENSHOT PLACEHOLDER
IMAN Knowledge Map · Progress Report · April 2026

## Slide 3
A 30-Year Life Expectancy Gap Demands Faster Research-to-Action
3 / 11
The gap, defined: Residents of Englewood and Chicago Lawn (South Side) live on average 30 fewer years than residents of Streeterville — a 5-mile drive away.
The bottleneck is not a lack of evidence — it is the speed of connecting evidence to action:
Research is scattered
Hundreds of studies across journals, databases, and grey literature — no single place to look
Manual review is slow
Identifying the highest-impact intervention for one domain takes weeks of literature review
Cross-domain decisions require rare expertise
Connecting funding, programming, and evidence across 9 domains simultaneously requires a team
SCREENSHOT PLACEHOLDER
(Life expectancy map or
gap visualization)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 4
The Knowledge Map Connects 250 Studies to Decisions in Seconds
4 / 11
Knowledge Map, defined:
A structured database of peer-reviewed research, organized by intervention domain, with quantified life-expectancy impact estimates and cost ranges — so any team member can find the best evidence for a decision in seconds, not weeks.
The 9 intervention domains covered:
Healthcare
Housing & Community Building
Food Access
Education & Youth Development
Funding
Mobility & Transit
Recreation & Community
Other City Projects
IMAN Initiatives
SCREENSHOT PLACEHOLDER
(Knowledge Map folder
structure or diagram)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 5
Milestone 1: 250 Studies Are Organized, Categorized, and Listenable
5 / 11
WHAT WAS DONE
250 peer-reviewed studies and articles downloaded
One PDF per study, filed by domain — no duplicates, no dead links
Organized across 9 intervention domains with impact estimates
Each study tagged by topic, evidence quality, and life-expectancy impact estimate
One audio podcast generated per study using NotebookLM
Google AI tool that converts each PDF into a 10–15 min conversational audio summary
250 studies · 9 domains · 250 audio podcasts generated
SCREENSHOT PLACEHOLDER
(NotebookLM interface or
folder structure)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 6
Milestone 2: The Full Library Is Accessible From One Google Drive Link
6 / 11
WHAT WAS DONE
All 250 PDFs and audio podcasts uploaded to Google Drive
Organized in the same 9-domain folder structure as the knowledge map
Accessible to any team member with a shared link
No installation or technical setup — any web browser works
Single source of truth for the entire research library
Additions and updates are reflected immediately for all users with access
One link · Full library · Always up to date
SCREENSHOT PLACEHOLDER
(Google Drive folder
view)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 7
Milestone 3: A 7-Person Team Can Now Build Evidence-Based Deliverables in Minutes
7 / 11
WHAT WAS DONE
Knowledge map pushed to GitHub — a shared, version-controlled codebase
Every change is tracked and reversible; no one overwrites anyone else's work
Cloud environment provisioned for 7 consultants and IMAN staff
Each user gets an AI assistant that reads the full knowledge map and generates reports on demand
Research-to-deliverable time reduced from days to minutes
A funding brief drawing on 3 domains of evidence can be drafted in a single AI prompt
7 consultants · IMAN staff · One shared AI environment
SCREENSHOT PLACEHOLDER
(GitHub repo or Claude
Code interface)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 8
Milestone 4: IMAN's Own Program Data Is Now Searchable Alongside External Research
8 / 11
WHAT WAS DONE
IMAN's collected program data added to the Data Library
Includes IMAN initiative profiles, outcomes data, and program documentation
Internal data is now queryable alongside peer-reviewed evidence
Team members can cross-reference IMAN's program results against the evidence base in one query
Enables direct comparison: what IMAN does vs. what research recommends
Surfaces gaps, validates current programs, and identifies new opportunities
IMAN programs · IMAN outcomes · 250 cross-referenced studies
SCREENSHOT PLACEHOLDER
(Data Library folder or
IMANinitiative profile)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 9
Milestone 5: SME Outreach Underway — 200 of 700 Experts Contacted So Far
9 / 11
WHERE THINGS STAND
200 of 700 identified subject-matter experts (SMEs) contacted by email
Researchers, practitioners, and policy experts across the 9 intervention domains
Outreach designed to capture insights that published research lags behind
Peer-reviewed studies lag real-world practice by 3–7 years; expert input closes that gap
500 additional experts remain in the contact pipeline — outreach is ongoing
All responses will be integrated as a curated expert insights layer alongside the research evidence
200 contacted · 500 remaining · Outreach ongoing
SCREENSHOT PLACEHOLDER
(Email template or
SME contact list)
IMAN Knowledge Map · Progress Report · April 2026

## Slide 10
All Five Milestones Complete as of April 2026
10 / 11
1
Research
Foundation
250 PDFs
9 domains
250 podcasts
2
Google Drive
Published
Library
accessible
to all users
3
GitHub +
Cloud Env
7 consultants
+ IMAN staff
enabled
4
IMAN Data
Integrated
Internal data
joins the
library
5
SME
Outreach
200 of 700
expert contacts
made (ongoing)
✓ All milestones complete · April 2026
IMAN Knowledge Map · Progress Report · April 2026

## Slide 11
Two Workstreams Built, Two In Progress — One Pending IMAN Input
11 / 11
01
Agent Skills — Built, Being Refined
7 skills developed and deployed; currently being refined and polished for consistent production use across the team
02
Two BPMNs Created — Research + Network Expansion
Social Impact Researcher research workflow and network expansion / lead-generation workflow are mapped and documented
03
Social Impact Researcher Job Description
To be drafted after reviewing IMAN's corporate structure and existing role formats — flagged for discussion at next meeting
04
Weekly Newsletter From the Knowledge Base
Automated newsletter that scans the database for new evidence and opportunities, then surfaces project ideas for IMAN staff — in development
SCREENSHOT PLACEHOLDER
(Roadmap, process flow,
or next-step diagram)
IMAN Knowledge Map · Progress Report · April 2026